## Sheet1
	Project Tracker:

	Date	Aspect of the Project	Approx. time spent	What was accomplished	What needs to be done	Info learned
	2020-05-06	organization	20 min	I found some images of the project prior to its current state.	The delivery of 2N2222s needs to come (on Monday)	I am not very well organized
	2020-05-06	Software	5 min	I made the software slightly better by adding comments and adding a histogram feature.	The delivery of 2N2222s needs to come (on Monday)	How to change MatPlotLib themes
	2020-05-07	hardware	45 min	I optimized the design of the PWM averager circuit (Speaker Driver Rev. #2) with LTSpice	ditto	The mobile app I used as a substitute for LTSpice was no match to LTSpice.
	2020-05-07	organization	3 hrs	I located previous sources that I used when learning information before & learned APA & wrote intro	''	APA format and IMRaD format
	2020-05-08	hardware	10 min	I attatched the apparantly high impedance control line from the power supply to an i/o on the arduino	'' & GUI for the software
	2020-05-08	Software	2 hrs	I designed a GUI in QT Designer for my software.		GridLayouts in PyQt are much better than the equivalent of a poor constraint layout!
	2020-05-08	Software	2 hrs	I worked on re-writing my original code to use this GUI.
	2020-05-09	Software	4-5 hrs	I worked on re-writing the software for the GUI (mostly the scanning feature)		Threading w/ PyQt requires signals. (QObjects cannot be accessed from another thread.)
	2020-05-10	Software	4-6 hrs	Worked on software... Finished scanning, wrote output code, a few other improvements		Matplotlib inside PyQt4 widgets / QDockWidgets are a pain
	2020-05-10	hardware	2 hrs	Drew a scematic for the laser driver (couldn't find the original), noticed some GNDing issues & fixed	PWM averaging circuit!	PSU control line pushes the limit of what an Arduino's i/os can handle... Though Arduino Nano's are tough!!
	2020-05-11	hardware	3+ hrs	Tested the laser driver after a few improvements yesterday, Made PWM averager & tested it		The smell that the power supply makes when something is shorted and something inside is burning. Fun. Also the smell of burning whatever is in modern 1K POTs! & the need for differential voltage probes, which I don't have.
	2020-05-11	Software	1.5 hrs	Finished up the software-- for now	Fix the lens smoother arduino code-- maybe have that on the LSM class
	2020-05-12	hardware	2 hrs	Put PWM averager on perfboard, soldered it in/installed it, and tested it
	2020-05-13	soft+hard	15 min	Tried scanning, didn't work that great	Investigate the streaks that go through the scan
	2020-05-14	soft+hard	2 hrs	I beefed up the power wires (too resistive for the current) and I made the intensity readings more accurate (in the code)		Although CAT-5 cable handles current better than I would have thought, yeah, it cannot do 500+mA (need ~1500mA)
	2020-05-16	soft+hard	~3 hrs	I finally got it to work!!!!!!!!!!!!! There were some software and hardware problems, I added a POT across the cap in the PWM averager.		The streaks through the scan were not a result of inconsistent hardware, but of improper image formatting!
	2020-05-17	soft+hard	~2 hrs	Worked on correction for the nonlinearity of the speaker's movement
	2020-05-18	soft+hard	~1.25 hrs	Did further testing, soldered in the trim pot for the PWM averager, etc.
	2020-05-19	Software	~2-3 hrs	Added software support for scans with multiple focal planes, replaced springy wire that held the specimen w/ the stage from an old microscope		I need a real microscope stage... The slippery plastic lens thing on the front of the optical sensor is inadequate.
	2020-05-20	soft+hard	3 hrs	I created a stage (modified from an old optical microscope) and added some bells and whistles in the software		There's a GNOME tool for making .desktops,
	2020-05-21	Software	30 min	Added the option to lay scan frames on top of each other with alpha values, and tired scanning some more.
	2020-05-22	soft+hard	30 min	Did more testing. I ned stage clips!	Stage clips	Stage clips actually do serve a purpose in microscopes
	5/23/2020	Software	2-3 hrs	fixed scanning issue... tried running more scans		how to copy a list in Python (index=:) / you need to in order to append it to another.
	2020-05-24	Software	4-5 hrs	Fixed image indexing issue... Higher -res scan of plant lice. re-wrote scanning code to use threading, faster& better	long scan left overnight. will check it tomorrow!	Python threading, matplotlib likes numpy arrays better than lists of floats.
	2020-05-23	soft+hard	2-3 hrs	Did more testing, tried higher wait times between pixels, experimented with focus	More testing. Last night's scan went poorly because of bad focus and more.	Focus is not to be ignored (although it's easy to ignore).
	2020-05-26	Software	2-3 hrs	Realized that I needed better image processing for the intensity detection, so I concocted a better function for that... Still needs work	More work on detector function
	2020-05-27	soft+hard	6 hrs	I made the intensity measurements less prone to error due to reflections by using a Gaussian blur on the image. Then the X-axis broke. After a while spent trying to think of better ways to actuate the X-axis, I settled upon using a microservo, which I built and then decided to fix the original because using a microservo would cut my resolution by 4-5x.		Using blurs and filters in OpenCV, finding brightest/dimmest spot in an image with OpenCV, and more (including that I shouldn't touch the X-axis speaker)!
	2020-05-28	soft+hard	~3 hrs	I beefed up the mechanical connection of the speaker for the X-axis... Almost ready to do some final scans, I hope!!!!	More testing/final scans for the project
	2020-05-30	soft+hard	10 min	Did more scans
	2020-06-01	soft+hard	1 hr	Scans, X-axis fiddling
	2020-06-02	organization	30 min	Pictures
	2020-05-28	organization	45 min	Added more pictures, worked on Glossary, References, Results
	2020-06-04	organization	2-3 hrs	ADded more pictures, in-text citations are done, made a video demonstrating the microscope, and did some basic editing	I pretty much just need to finish editing the paper, and then I will be done!
	2020-06-07	organization	10 min	Finished up the glossary
	2020-06-08	organization	2-3 hrs

	4.17*np.exp(0.016*%i)	-87.5+62.3*ln()

0	0	0
127.5	30	1.5
161.5	60	1.9
191.25	90	2.25
212.5	120	2.5
225.25	150	2.65
238	180	2.8
246.5	210	2.9
254	240	3
255	255	3